## CC LOB Estimates break down
ClaimCenter LOB (with OneInc accelerator install) - BA, DEV and QA - EFFORT BREAKUPS
Initial rough config WAG for the 4 self-contained pieces of work, to be discussed further:
Toyota Self Insured from iVos to CC
Points
OneInc config support for bank account handling and payments screens (3 separate additional accounts for Toyota SI) | 13
Bulk invoice – combined check TSI med daily payments (to include hooking up bulk UI to OneInc to issue) | 34
Integration support for Genex | 8
Policy input and claim adjudication (turn back on and regression all that was done, and finish what wasn’t done) | 55
Migration support | 5
115
Vendor Management from iVos to CC/CM – make CM system of record
Points
Enable vendor creation in CC and push to CM | 21
Enable duplicate match search in CM | 13
Enable vendor record review and update approval in CM | 13
Enable automated sync from CM to CC (business probably only wants Tax ID sync, not phone/address) | 8
Integration support for GIACT | 8
Integration support for vendor sync with One Inc | 8
71
Location Coding from iVos to CC
Points
Create location code screens/rules/datamodel in CM | 34
Update location code screens/rules/datamodel in CC | 13
Enhancements and fixes to existing functionality | 13
Integration support for webservice build | 8
Migrate existing location structure from Ivos to CM | 21
89
One Inc accelerator install and updates for CC
Points
Install accelerator into POC environment | 13
Review and updates to screens/batches/rules/datamodel after accelerator POC up and running | 34
New feature adoption | 21
Integration support | 8
OneInc CP4 platform update | 21
97
Total Story Points - CC Configuration | 372
Vendor availability and dependencies | 40
Total Story Points for CC Configuration -> BA+DEV+QA - In Sprint work | 412

## Conversion Estimates break down
Scope | Approach - Sample Query Filter condition | Quick Summary
Add conditions to include claim numbers for Toyota Self Insured (CMT_IN and ClaimCenter) – Needs DEV (Target loading) and QA efforts. | Inner Join #RequiredclaimstoMigrate where Pol.insurer_number in ('0005','0006','TMMK', 'TMMWV') and CL.insurance_type = 2 | We will extract Required claims based on the scope from stage and we will use that table join to control the claims which we want to load. POC was complete. No BA work is anticipated considering the agreed approach.
Task/Action | Go-Live Date | Owner | Effort (Story Points) | Comments
Set up Azure environments (if paused) | Future release | MSIG Infra |  | Prerequisite
Test CICD pipelines for code deployment | Future release | MSIG Infra |  | Prerequisite
Refresh Ivos Stage database | Future release | MSIG IVOS |  | Prerequisite
Refresh commonly used tables for Toyota Self insured (Target Loading) | Future release | ACN | 10
Address deferred defects and Resolve | Future release | ACN/MSIG | 30 | Assuming a maximum of ~10 defects. If there will be more defects, effort is subject to increase depending on the complexity.
Conversion Support from Configuration | Future release | ACN | 20
Rework of entities | Future release | ACN/MSIG |  | There is no rework considered as of now. If any rework needed that will be estimated seperately.
Test ETL flow | Future release | ACN | 10
QA Reconciliation | Future release | ACN | 30
Total Story Points for Claim Conversion -> BA+DEV+QA - In Sprint work |  |  | 100

## Effort Summary
Option 3 | Moving Toyota Self Insured to ClaimCenter Cloud and then switch to One Inc | Location Code and Vendor Management continue to be on iVOS
Story Points
| Areas | Original Scope (Story Points) | Modification Required (Story Points) | Net New Addition (Story Points) | Notes
| ClaimCenter LOB (with OneInc accelerator install) - BA, DEV and QA | 42 | 412 | 370 | Karthik K - Please work with Tech leads, Stef 04/04 - Karthik K - DONE
| Claim Conversion - BA, DEV and QA (Excluding the Prerequisites) | 5 | 100 | 95 | Karthik K - Please work with Tech leads, Stef 04/04 - Karthik K - DONE
| Claims Integration |  |  |  | Tammy - Please work with integration leads
| Legacy Integrations |  |  |  | Anandhi - Please update legacy integration
| EDP |  |  |  | Sree - To understand this requirements and provide an update
|  | 47 | 512 | 465

## Modification Needs
Areas | Modification Needs required for the descoped features for TSI to bring back | Story Points
ClaimCenter LOB
CC Integrations | Genex should be fully built if OneInc Accelarator is coming in before TSI

## New Work Required
Areas | New work | Stort Points
ClaimCenter LOB
CC Integrations
OneInc Accelarator | New work, should we do this before TSI? What is the effort and time required? What are the dependencies we have to do this before TSI
Integrations | If OneInc Accelarator is added before TSI no legacy integration is in picture, all integration through CC and to EDP
EDP | EDP work required for treasury if OneInc accelarator in place